## Project Timeline
YOUR PROJECT
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2015-08-31 | Project Start | -5 | 1
2015-09-07 | Team Meeting; 1st homework started | 5 | 1
2015-09-14 | Homework #1 Due! | 10 | 1
2015-09-21 | Homework #2 Due | 15 | 1
2015-09-28 | Homework #3 Due | 20 | 1
2015-10-05 | UML diags final; proj plan final | 5 | 1
2015-10-12 | Database design draft | 10 | 1
2015-10-19 | Mid-semester peer reviews due | 15 | 1
2015-10-26 | Draft IT requirements, including network design | 5 | 1
2015-11-02 | Homework #4 Due | 10 | 1
2015-11-09 | First Demo of Prototype | -5 | 1
2015-11-16 | User Validation & Test plan finalized | 10 | 1
2015-11-23 | Client Visit | -5 | 1
2015-11-30 | Draft Documentation | 5 | 1
2015-12-07 | Paper Due - Final Documentation | 10 | 1
2015-12-14 | FINAL PRESENTATION! | -5 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes
2015-08-31 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All
2015-08-31 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All
2015-08-31 | Project Start | Further develop this project plan (it is part of HW1) - THINK through your time management and what you will accomplish as the weeks progress. | All
2015-09-04 | Team Meeting; 1st homework started | Team meeting to complete draft of project plan | All
2015-09-07 | Use Case | Use case complete | All
2015-09-13 | Complete HW 1 + Prepare for Client meeting | Complete HW 1 Finalize Use Case Finalize Project plan Compile client questions | All
2015-09-14 | Homework #1 Due! | Have HW1 done; Have this project plan completely filled in for review and comments back so you will know if you have a good plan to get to end-game; Have your client questionnaire finalized and be prepared to interview the client. | All
2015-09-18 | ERD Complete | Complete ERD | All
9/19-9/20 | ERD Documentation Complete | Documentation for ERD | Paul
9/19-9/20 | Draft Wireframe | Wireframe Discussion Initialize wireframe layout | Dev Team
2015-09-21 | Homework #2 Due | E-R diagrams complete with supporting documentation if explanation is required for anything you document in your diagrams.
2015-09-25 | Mock-ups Complete | Complete wireframe mock-ups! | Dev team
9/26-9/27 | Documentation Complete | Documentation for Mock-ups | Paul
2015-09-28 | Homework #3 Due | Complete mock-ups (ie. wireframes) of your user interface.
2015-09-28 | Delagate weekly tasks | Give specific tasks before meeting Friday | All
2015-10-02 | Finalization (Project plan) | Make final edits to project plan (other) | All
2015-10-05 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams
10/6-10/8 | Begin Database Design | fill me in…
2015-10-09 | Finalize Database Draft | Meeting to Finalize Database draft | All
2015-10-12 | Database design draft | Draft database design
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-10-19 | Mid-semester peer reviews due | Complete initial (ie. first pass feedback) peer reviews
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-10-26 | Draft IT requirements, including network design
| fill me in… | fill me in…
| fill me in… | fill me in…
2015-11-02 | Homework #4 Due | Database prototype complete
2015-11-09 | First Demo of Prototype | Complete project prototype first-pass demo ready
2015-11-16 | User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented
2015-11-23 | Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented
2015-11-30 | Draft Documentation | All documentation required for the project in Draft form
2015-12-07 | Paper Due - Final Documentation | All documentation required for the project in FINAL form
2015-12-07 | Final Peer Evaluations | Complete final peer evaluation forms and submit | All
2015-12-14 | FINAL PRESENTATION! | Git er dun! | All

## Week Class Sched - Fall2015
Week | Class Topics and Activities | Assignments Due | Class Format
8/31 | Introduction; Project case study; Project plan; |  | Group (HC2023)
Sections and Teams; Project overview
9/7 | NO CLASS: Labor Day
9/14 | Client Interview | Homework 1 due | Group (HC2023)
9/21 | SME visit | Team status report
Brown bag session
Homework 2 due
9/28 | Project Management and UML | Team status report | Group (HC2023)
Brown bag session
Homework 3 due
10/5 | Guest presentation: Alan Labouseur - database | Team status report | Group (HC2023)
Brown bag session
10/12 |  | Team status report | HC2023 available
|  | Brown bag session | if needed
10/19 | Networking | Team status report | Group (HC2023)
| Draft peer-reviews | Brown bag session
10/26 |  | Team status report
Brown bag session
11/2 |  | Team status report: Database | HC2023 available
|  | Homework 4 due | if needed
11/9 | Prototype 1st Demonstration | Rough draft demo presentations
11/16 | User Validation & Test Planning | Team status report | Group (HC2023)
Brown bag session
11/23 | Client visit | Team status report
Brown bag session
11/30 | SME visit | Team status report
| Draft documentation / paper | Brown bag session
12/7 | Final documentation / paper | Brown bag session
| Final peer-reviews | Project paper due
Peer evaluations due
12/14 | Project presentations | Project prototype due
Project presentations

## Weekly Status Reports
Status Report - Team name, members
Date
RGY | Item | Description | Mitigation / Help needed
Red
Yellow
Green