## Project Timeline
YOUR PROJECT
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2015-08-31 | Project Start | -5 | 1
2015-09-07 | Team Meeting; 1st homework started | 5 | 1
2015-09-14 | Homework #1 Due! | 10 | 1
2015-09-21 | Homework #2 Due | 15 | 1
2015-09-28 | Homework #3 Due | 20 | 1
2015-10-05 | UML diags final; proj plan final | 5 | 1
2015-10-12 | Database design draft | 10 | 1
2015-10-19 | Mid-semester peer reviews due | 15 | 1
2015-10-26 | Draft IT requirements, including network design | 5 | 1
2015-11-02 | Homework #4 Due | 10 | 1
2015-11-09 | First Demo of Prototype | -5 | 1
2015-11-16 | User Validation & Test plan finalized | 10 | 1
2015-11-23 | Client Visit | -5 | 1
2015-11-30 | Draft Documentation | 5 | 1
2015-12-07 | Paper Due - Final Documentation | 10 | 1
2015-12-14 | FINAL PRESENTATION! | -5 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes
2015-08-31 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All
2015-08-31 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All
2015-08-31 | Project Start | Further develop this project plan (it is part of HW1) - THINK through your time management and what you will accomplish as the weeks progress. | All
2015-09-04 | Team Meeting; 1st homework started | Team meeting to complete draft of project plan | All
2015-09-07 | Use Case | Use case complete | All
2015-09-13 | Complete HW 1 + Prepare for Client meeting | Complete HW 1 Finalize Use Case Finalize Project plan Compile client questions | All
2015-09-14 | Homework #1 Due! | Have HW1 done; Have this project plan completely filled in for review and comments back so you will know if you have a good plan to get to end-game; Have your client questionnaire finalized and be prepared to interview the client. | All
2015-09-18 | ERD Complete | Complete ERD | All
9/19-9/20 | ERD Documentation Complete | Documentation for ERD | Paul
9/19-9/20 | Draft Wireframe | Wireframe Discussion Initialize wireframe layout | Dev Team
2015-09-21 | Homework #2 Due | E-R diagrams complete with supporting documentation if explanation is required for anything you document in your diagrams.
2015-09-25 | Mock-ups Complete | Complete wireframe mock-ups! | Dev team
2015-09-27 | Documentation Complete | Documentation for Mock-ups completed | Paul
2015-09-28 | Homework #3 Due | Complete mock-ups (ie. wireframes) of your user interface. | All
2015-10-02 | Finalization (UML) | Finish the UML | Paul
2015-10-02 | Finalization (Project plan) | Make final edits to project plan (other) | All
2015-10-05 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams | All
2015-10-06 | Begin Database Design | Create initial database mockup | All
2015-10-09 | Finalize Database Draft | Finalize Database draft | Dev Team
2015-10-12 | Build initial UI | Implement initial UI from mockups | Dev Team
2015-10-16 | Document UI | Documentation of initial UI | Paul
2015-10-16 | Have Network design specfications complete | Have all specifications identified | Dev Team + Matt Marak.
2015-10-19 | Mid-semester peer reviews due | Complete initial (ie. first pass feedback) peer reviews | All
2015-10-23 | Network design finalized | Finalize IT requirements and Network design drafts | Matt Marak.
2015-10-25 | Documentation of network design | Document network design | Paul
2015-10-28 | IT Hardware installed | Hardware setup + server setup External dependencies installed and configured | Matt Marak.
2015-10-30 | Database built and tested | Database initialized and confirmed operational | All
2015-11-02 | Homework #4 Due | Database prototype complete
2015-11-09 | First Demo of Prototype | Complete project prototype first-pass demo ready
2015-11-16 | User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented
2015-11-23 | Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented
2015-11-30 | Draft Documentation | All documentation required for the project in Draft form
2015-12-07 | Paper Due - Final Documentation | All documentation required for the project in FINAL form
2015-12-07 | Final Peer Evaluations | Complete final peer evaluation forms and submit | All
2015-12-14 | FINAL PRESENTATION! | Put em in a coffin entire thing is AWPerational | All

## Week Class Sched - Fall2015
Week | Class Topics and Activities | Assignments Due | Class Format
8/31 | Introduction; Project case study; Project plan; |  | Group (HC2023)
Sections and Teams; Project overview
9/7 | NO CLASS: Labor Day
9/14 | Client Interview | Homework 1 due | Group (HC2023)
9/21 | SME visit | Team status report
Brown bag session
Homework 2 due
9/28 | Project Management and UML | Team status report | Group (HC2023)
Brown bag session
Homework 3 due
10/5 | Guest presentation: Alan Labouseur - database | Team status report | Group (HC2023)
Brown bag session
10/12 |  | Team status report | HC2023 available
|  | Brown bag session | if needed
10/19 | Networking | Team status report | Group (HC2023)
| Draft peer-reviews | Brown bag session
10/26 |  | Team status report
Brown bag session
11/2 |  | Team status report: Database | HC2023 available
|  | Homework 4 due | if needed
11/9 | Prototype 1st Demonstration | Rough draft demo presentations
11/16 | User Validation & Test Planning | Team status report | Group (HC2023)
Brown bag session
11/23 | Client visit | Team status report
Brown bag session
11/30 | SME visit | Team status report
| Draft documentation / paper | Brown bag session
12/7 | Final documentation / paper | Brown bag session
| Final peer-reviews | Project paper due
Peer evaluations due
12/14 | Project presentations | Project prototype due
Project presentations

## Weekly Status Reports
Status Report - Team name, members
Date | 2015-09-05
RGY | Item | Description | Mitigation / Help needed
Red | Documentation | Looking for what the layout should look like | Should the documentation be in one massive pdf or separate word docs? Also is there a certain way they should be laid out?
Yellow | Project plan | Our layout and milestones | We had a long discussion about if the milestones are duedates or if they are more of a meeting schedule.
Green